## Burndown Chart Sprint1
Sprint 1 Burndown Chart
Sprint 1
Task ID | Descrição da Tarefa | Estimativa Inicial | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19
|  | Dia 0 | Dia 1 | Dia 2 | Dia 3 | Dia 4 | Dia 5 | Dia 6 | Dia 7 | Dia 8 | Dia 9 | Dia 10 | Dia 11 | Dia 12
1 | T1: Play the first area of the game | 3 | bar: 2025-10-11; 2025-10-15
4 | T2: Read through the classes in the codebase. | 6 | 2025-10-09: 1; 2025-10-12: 1.5; 2025-10-13: 0.2; 2025-10-15: 0.4; 2025-10-16: 0.4
10 | T3: Define roughly functionality 1. | 1 | 2025-10-10: 0.2; 2025-10-11: 0.4; 2025-10-12: 0.2; 2025-10-13: 0.1; 2025-10-14: 0.1
11 | T4: Define roughly functionality 2. | 1 | 2025-10-14: 0.5; 2025-10-15: 0.5
12 | T5: Define roughly functionality 3. | 1 | 2025-10-14: 0.2; 2025-10-17: 0.5; 2025-10-18: 0.3
13 | T6: Trial modification of code. | 2 | 2025-10-14: 1; 2025-10-15: 0.7; 2025-10-16: 0.3
Esforço Completo |  | 0 | 0 | 1 | 0.2 | 1.4 | 1.7 | 0.3 | 1.8 | 2.6 | 0.7 | 0.5 | 0.3 | 0
Esforço Restante |  | 14 | 14 | 13 | 12.8 | 11.4 | 9.7 | 9.4 | 7.6 | 5 | 4.3 | 3.8 | 3.5 | 3.5
Burndown Ideal |  | 14 | 12.8333 | 11.6667 | 10.5 | 9.3333 | 8.1667 | 7 | 5.8333 | 4.6667 | 3.5 | 2.3333 | 1.1667 | 0

## Burndown Chart Sprint2
Sprint 2 Burndown Chart
Sprint 2
Task ID | Descrição da Tarefa | Estimativa Inicial | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26
|  | Dia 0 | Dia 1 | Dia 2 | Dia 3 | Dia 4 | Dia 5 | Dia 6 | Dia 7
1 | T1: Play the first area of the game | Dia 0: 0.5; Dia 1: 0.1
2 | T2: Read through the classes in the codebase. | Dia 0: 1; Dia 1: 0.3; Dia 3: 0.3; Dia 4: 0.4
7 | T7: Make feature goals more specific. | Dia 0: 0.5; Dia 1: 0.2; Dia 2: 0.2; Dia 3: 0.1
8 | T8: Brainstorm further features for replacement (if necessary). | Dia 0: 1; Dia 3: 0.2; Dia 4: 0.2; Dia 5: 0.1
9 | T9: Study code associated to undo/redo feature | Dia 0: 1; Dia 6: 0.5; Dia 7: 0.5
11 | T10: Study code associated to water piping system. | Dia 0: 1; Dia 1: 0.2
12 | T11: Define functionality 1 | Dia 0: 0.5; Dia 1: 0.2; Dia 2: 0.2; Dia 3: 0.1
13 | T12: Define functionality 2. | Dia 0: 0.5; Dia 4: 0.25; Dia 5: 0.25
14 | T13: Define functionality 3. | Dia 0: 0.5; Dia 4: 0.25; Dia 5: 0.25
Esforço Completo |  | 0 | 1 | 0.4 | 0.7 | 1.1 | 0.6 | 0.5 | 0.5
Esforço Restante |  | 6.5 | 5.5 | 5.1 | 4.4 | 3.3 | 2.7 | 2.2 | 1.7
Burndown Ideal |  | 6.5 | 5.5714 | 4.6429 | 3.7143 | 2.7857 | 1.8571 | 0.92857 | 0

## Burndown Chart Sprint3
Sprint 3 Burndown Chart
Sprint 3
Task ID | Descrição da Tarefa | Estimativa Inicial | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02
|  | Dia 0 | Dia 1 | Dia 2 | Dia 3 | Dia 4 | Dia 5 | Dia 6 | Dia 7
1 | T1: Play the first area of the game | Dia 0: 0.1; Dia 6: 0.1 | DONE | 0.1 | Carolina | 11
11 | T11: Study code associated to water piping system. | Dia 0: 0.5; Dia 1: 0.25 | NOT ENOUGH WORK YET | 0.25 | Diogo | 12
14.1 | T14.1: Revisit the read code, and find code smells. | Dia 0: 0.5; Dia 2: 0.25; Dia 6: 0.1; Dia 7: 0.15 | DONE | 0.5 | Gabriela | 14
14.2 | T14.2: Revisit the read code, and find code smells. | Dia 0: 0.5; Dia 5: 0.25; Dia 6: 0.25 | DONE | 0.5 | Diogo | 14
14.3 | T14.3: Revisit the read code, and find code smells. | Dia 0: 0.5; Dia 1: 0.25; Dia 6: 0.25 | DONE | 0.5 | Gabriel | 14
14.4 | T14.4: Revisit the read code, and find code smells. | Dia 0: 0.5; Dia 4: 0.25; Dia 7: 0.25 | DONE | 0.5 | Carolina | 14
14.5 | T14.5: Revisit the read code, and find code smells. | Dia 0: 0.5; Dia 6: 0.25 | NOT ENOUGH WORK YET | 0.25 | Dinis | 14
14.6 | T14.6: Revisit the read code, and find code smells. | Dia 0: 0.5; Dia 2: 0.25; Dia 3: 0.25 | DONE | 0.5 | Manel | 14
15.1 | T15.1: Document found code smells, and brainstorm possible solutions. | Dia 0: 0.5; Dia 7: 0.2 | NOT ENOUGH WORK YET | 0.2 | Gabriela | 15
15.2 | T15.2: Document found code smells, and brainstorm possible solutions. | Dia 0: 0.5; Dia 6: 0.25; Dia 7: 0.2 | NOT ENOUGH WORK YET | 0.45 | Diogo | 15
15.3 | T15.3: Document found code smells, and brainstorm possible solutions. | Dia 0: 0.5; Dia 5: 0.1; Dia 6: 0.3 | NOT ENOUGH WORK YET | 0.4 | Gabriel | 15
15.4 | T15.4: Document found code smells, and brainstorm possible solutions. | Dia 0: 0.5; Dia 4: 0.2; Dia 7: 0.2 | NOT ENOUGH WORK YET | 0.4 | Carolina | 15
15.5 | T15.5: Document found code smells, and brainstorm possible solutions. | Dia 0: 0.5 | NOT STARTED | 0 | Dinis | 15
15.6 | T15.6: Document found code smells, and brainstorm possible solutions. | Dia 0: 0.5; Dia 4: 0.25; Dia 5: 0.1 | NOT ENOUGH WORK YET | 0.35 | Manel | 15
16.1 | T16.1: Revisit the read code, and find design patterns. | 0.5 |  | 0.1 | 0.1 |  |  | 0.1 | 0.2 | DONE | 0.5 | Gabriela | 16
16.2 | T16.2: Revisit the read code, and find design patterns. | Dia 0: 0.5; Dia 5: 0.1; Dia 6: 0.2; Dia 7: 0.2 | DONE | 0.5 | Diogo | 16
16.3 | T16.3: Revisit the read code, and find design patterns. | 0.5 | 0.1 |  |  |  | 0.1 | 0.1 | 0.2 | DONE | 0.5 | Gabriel | 16
16.4 | T16.4: Revisit the read code, and find design patterns. | Dia 0: 0.5; Dia 7: 0.25 | NOT ENOUGH WORK YET | 0.25 | Carolina | 16
16.5 | T16.5: Revisit the read code, and find design patterns. | Dia 0: 0.5 | NOT STARTED | 0 | Dinis | 16
16.6 | T16.6: Revisit the read code, and find design patterns. | Dia 0: 0.5; Dia 2: 0.25 | NOT ENOUGH WORK YET | 0.25 | Manel | 16
17.1 | T17.1: Find code blocks, where some design patterns may be implemented. | Dia 0: 0.5; Dia 2: 0.25; Dia 6: 0.25 | DONE | 0.5 | Gabriela | 17
17.2 | T17.2: Find code blocks, where some design patterns may be implemented. | Dia 0: 0.5; Dia 5: 0.2; Dia 6: 0.2; Dia 7: 0.1 | DONE | 0.5 | Diogo | 17
17.3 | T17.3: Find code blocks, where some design patterns may be implemented. | Dia 0: 0.5; Dia 5: 0.2; Dia 6: 0.2; Dia 7: 0.1 | DONE | 0.5 | Gabriel | 17
17.4 | T17.4: Find code blocks, where some design patterns may be implemented. | Dia 0: 0.5; Dia 7: 0.2 | NOT ENOUGH WORK YET | 0.2 | Carolina | 17
17.5 | T17.5: Find code blocks, where some design patterns may be implemented. | Dia 0: 0.5 | NOT STARTED | 0 | Dinis | 17
17.6 | T17.6: Find code blocks, where some design patterns may be implemented. | Dia 0: 0.5; Dia 2: 0.25 | NOT ENOUGH WORK YET | 0.25 | Manel | 17
18.1 | T18.1: Document found design patterns, and think about possible improvements. | Dia 0: 0.5; Dia 6: 0.25; Dia 7: 0.15 | NOT ENOUGH WORK YET | 0.4 | Gabriela | 18
18.2 | T18.2: Document found design patterns, and think about possible improvements. | Dia 0: 0.5; Dia 6: 0.15; Dia 7: 0.15 | NOT ENOUGH WORK YET | 0.3 | Diogo | 18
18.3 | T18.3: Document found design patterns, and think about possible improvements. | Dia 0: 0.5; Dia 7: 0.4 | NOT ENOUGH WORK YET | 0.4 | Gabriel | 18
18.4 | T18.4: Document found design patterns, and think about possible improvements. | Dia 0: 0.5 | NOT STARTED | 0 | Carolina | 18
18.5 | T18.5: Document found design patterns, and think about possible improvements. | Dia 0: 0.5 | NOT STARTED | 0 | Dinis | 18
18.6 | T18.6: Document found design patterns, and think about possible improvements. | Dia 0: 0.5; Dia 5: 0.25 | NOT ENOUGH WORK YET | 0.25 | Manel | 18
Esforço Completo |  | 0 | 0.6 | 1.35 | 0.35 | 0.7 | 1.05 | 2.8 | 2.4
Esforço Restante |  | 15.6 | 15 | 13.65 | 13.3 | 12.6 | 11.55 | 8.75 | 6.35
Burndown Ideal |  | 15.6 | 13.3714 | 11.1429 | 8.9143 | 6.6857 | 4.4571 | 2.2286 | 0

## Burndown Chart Sprint4
Sprint 4 Burndown Chart
Sprint 4
| Task ID | Descrição da Tarefa | Estimativa Inicial | 2-nov.-25 | 3-nov.-25 | 4-nov.-25 | 5-nov.-25 | 6-nov.-25 | 7-nov.-25 | 8-nov.-25
|  |  | Dia 0 | Dia 1 | Dia 2 | Dia 3 | Dia 4 | Dia 5 | Dia 6 | Dia 7
$$ | 14.1 | T14.1: Revisit the read code, and find code smells. | Dia 0: 0.05; Dia 1: 0.05 | DONE | 0.05 | Gabriela | 14
| 14.5 | T14.5: Revisit the read code, and find code smells. | Dia 0: 0.25; Dia 1: 0.25 | DONE | 0.25 | Dinis | 14
| 14.6 | T14.6: Revisit the read code, and find code smells. | Dia 0: 0.1; Dia 1: 0.1 | DONE | 0.1 | Manel | 14
| 15.1 | T15.1: Document found code smells, and brainstorm possible solutions. | Dia 0: 0.3; Dia 1: 0.3 | DONE | 0.3 | Gabriela | 15
| 15.2 | T15.2: Document found code smells, and brainstorm possible solutions. | Dia 0: 0.05; Dia 1: 0.05 | DONE | 0.05 | Diogo | 15
| 15.3 | T15.3: Document found code smells, and brainstorm possible solutions. | Dia 0: 0.2; Dia 1: 0.2 | DONE | 0.2 | Gabriel | 15
| 15.4 | T15.4: Document found code smells, and brainstorm possible solutions. | Dia 0: 0.4; Dia 1: 0.4 | DONE | 0.4 | Carolina | 15
| 15.5 | T15.5: Document found code smells, and brainstorm possible solutions. | Dia 0: 0.5; Dia 1: 0.15; Dia 2: 0.35 | DONE | 0.5 | Dinis | 15
| 15.6 | T15.6: Document found code smells, and brainstorm possible solutions. | Dia 0: 0.15; Dia 1: 0.15 | DONE | 0.15 | Manel | 15
| 16.4 | T16.4: Revisit the read code, and find design patterns. | Dia 0: 0.25; Dia 1: 0.2; Dia 2: 0.05 | DONE | 0.25 | Carolina | 16
| 16.5 | T16.5: Revisit the read code, and find design patterns. | 0.5 | 0.1 | 0.3 | 0.05 | 0.05 |  |  |  | DONE | 0.5 | Dinis | 16
| 16.6 | T16.6: Revisit the read code, and find design patterns. | Dia 0: 0.25; Dia 1: 0.1; Dia 2: 0.15 | DONE | 0.25 | Manel | 16
| 17.4 | T17.4: Find code blocks, where some design patterns may be implemented. | Dia 0: 0.3; Dia 1: 0.2; Dia 2: 0.1 | DONE | 0.3 | Carolina | 17
| 17.5 | T17.5: Find code blocks, where some design patterns may be implemented. | 0.5 | 0.05 | 0.15 | 0.25 | 0.05 |  |  |  | DONE | 0.5 | Dinis | 17
| 17.6 | T17.6: Find code blocks, where some design patterns may be implemented. | Dia 0: 0.25; Dia 1: 0.05; Dia 2: 0.1; Dia 3: 0.1 | DONE | 0.25 | Manel | 17
| 18.1 | T18.1: Document found design patterns, and think about possible improvements. | Dia 0: 0.1; Dia 1: 0.05; Dia 2: 0.05 | DONE | 0.1 | Gabriela | 18
| 18.2 | T18.2: Document found design patterns, and think about possible improvements. | Dia 0: 0.2; Dia 1: 0.2 | DONE | 0.2 | Diogo | 18
| 18.3 | T18.3: Document found design patterns, and think about possible improvements. | Dia 0: 0.1; Dia 1: 0.1 | DONE | 0.1 | Gabriel | 18
| 18.4 | T18.4: Document found design patterns, and think about possible improvements. | Dia 0: 0.5; Dia 1: 0.25; Dia 2: 0.25 | DONE | 0.5 | Carolina | 18
| 18.5 | T18.5: Document found design patterns, and think about possible improvements. | 0.5 | 0 | 0.1 | 0.35 | 0.05 |  |  |  | DONE | 0.5 | Dinis | 18
| 18.6 | T18.6: Document found design patterns, and think about possible improvements. | Dia 0: 0.25; Dia 1: 0.1; Dia 2: 0.05; Dia 3: 0.1 | DONE | 0.25 | Manel | 18
| 19.1 | T19.1: Revisit the read code, and study the associated metrics. | Dia 0: 0.5; Dia 6: 0.5 | DONE | 0.5 | Gabriela | 19
| 19.2 | T19.2: Revisit the read code, and study the associated metrics. | Dia 0: 0.5; Dia 5: 0.25; Dia 6: 0.25 | DONE | 0.5 | Diogo | 19
| 19.3 | T19.3: Revisit the read code, and study the associated metrics. | Dia 0: 0.5; Dia 5: 0.25; Dia 6: 0.25 | DONE | 0.5 | Gabriel | 19
| 19.4 | T19.4: Revisit the read code, and study the associated metrics. | Dia 0: 0.5; Dia 6: 0.5 | DONE | 0.5 | Carolina | 19
| 19.5 | T19.5: Revisit the read code, and study the associated metrics. | Dia 0: 0.5; Dia 6: 0.5 | DONE | 0.5 | Dinis | 19
| 19.6 | T19.6: Revisit the read code, and study the associated metrics. | Dia 0: 0.5; Dia 6: 0.5 | DONE | 0.5 | Manel | 19
| 20.1 | T20.1: Document said metrics. | Dia 0: 0.5; Dia 6: 0.5 | DONE | 0.5 | Gabriela | 20
| 20.2 | T20.2: Document said metrics. | Dia 0: 0.5; Dia 6: 0.5 | DONE | 0.5 | Diogo | 20
| 20.3 | T20.3: Document said metrics. | Dia 0: 0.5; Dia 6: 0.5 | DONE | 0.5 | Gabriel | 20
| 20.4 | T20.4: Document said metrics. | Dia 0: 0.5; Dia 6: 0.5 | DONE | 0.5 | Carolina | 20
| 20.5 | T20.5: Document said metrics. | Dia 0: 0.5; Dia 6: 0.5 | DONE | 0.5 | Dinis | 20
| 20.6 | T20.6: Document said metrics. | Dia 0: 0.5; Dia 6: 0.5 | DONE | 0.5 | Manel | 20
| 21.1 | T21.1: Revisit the read code, and choose a part of the system to work on. | Dia 0: 0.5; Dia 4: 0.5 | DONE | 0.5 | Gabriela | 21
| 21.2 | T21.2: Revisit the read code, and choose a part of the system to work on. | Dia 0: 0.5; Dia 3: 0.25; Dia 4: 0.25 | DONE | 0.5 | Diogo | 21
| 21.3 | T21.3: Revisit the read code, and choose a part of the system to work on. | Dia 0: 0.5; Dia 3: 0.25; Dia 4: 0.25 | DONE | 0.5 | Gabriel | 21
| 21.4 | T21.4: Revisit the read code, and choose a part of the system to work on. | Dia 0: 0.5; Dia 4: 0.5 | DONE | 0.5 | Carolina | 21
| 21.5 | T21.5: Revisit the read code, and choose a part of the system to work on. | Dia 0: 0.5; Dia 4: 0.5 | DONE | 0.5 | Dinis | 21
| 21.6 | T21.6: Revisit the read code, and choose a part of the system to work on. | Dia 0: 0.5; Dia 4: 0.5 | DONE | 0.5 | Manel | 21
| 22.1 | T22.1: Develop the Use Case Diagram of the chosen system part. | Dia 0: 0.5; Dia 4: 0.15; Dia 5: 0.25; Dia 6: 0.1 | DONE | 0.5 | Gabriela | 22
| 22.2 | T22.2: Develop the Use Case Diagram of the chosen system part. | Dia 0: 0.5; Dia 3: 0.2; Dia 4: 0.2; Dia 5: 0.1 | DONE | 0.5 | Diogo | 22
| 22.3 | T22.3: Develop the Use Case Diagram of the chosen system part. | Dia 0: 0.5; Dia 2: 0; Dia 3: 0.2; Dia 4: 0.3 | DONE | 0.5 | Gabriel | 22
| 22.4 | T22.4: Develop the Use Case Diagram of the chosen system part. | Dia 0: 0.5; Dia 4: 0.1; Dia 5: 0.4 | DONE | 0.5 | Carolina | 22
| 22.5 | T22.5: Develop the Use Case Diagram of the chosen system part. | Dia 0: 0.5; Dia 5: 0.25; Dia 6: 0.25 | DONE | 0.5 | Dinis | 22
| 22.6 | T22.6: Develop the Use Case Diagram of the chosen system part. | Dia 0: 0.5; Dia 6: 0.5 | DONE | 0.5 | Manel | 22
| Esforço Completo |  | 0 | 3.05 | 1.65 | 1.75 | 3.4 | 1.5 | 6.35 | 0
| Esforço Restante |  | 17.7 | 14.7 | 13 | 11.3 | 7.9 | 6.4 | 0 | 0
| Burndown Ideal |  | 17.7 | 15.2 | 12.6 | 10.1 | 7.6 | 5.1 | 2.5 | 0

## Burndown Chart Sprint5
Sprint 5 Burndown Chart
Sprint 5
Task ID | Descrição da Tarefa | Estimativa Inicial | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16
|  | Dia 0 | Dia 1 | Dia 2 | Dia 3 | Dia 4 | Dia 5 | Dia 6 | Dia 7
23 | T23: Review and look into what a Use case diagram covering undo/redo added feature would look like. | 2 |  |  | 0.5 | 0.5 | 0.5 | 0.5 |  | DONE | 2
24 | T24: Review and look into what a Use case diagram covering leakage added feature would look like. | 2 |  |  | 0.5 | 0.5 | 0.5 | 0.5 |  | DONE | 2
25 | T25: Go over milestone 2 reviews and identify issues that can be worked on. | 2 | 0.5 |  | 0.5 | 0.5 | 0.4 | 0.1 |  | DONE | 2
26 | T26: identify areas of code relating to leaks. | Dia 0: 2; Dia 1: 2 | DONE | 2
27 | T27: Work on implementing US1 (Undo / Redo). | Dia 0: 3; Dia 1: 1; Dia 2: 1; Dia 3: 1 | DONE | 3
28 | T28: Work on implementing US2 (Leaks). | 2 |  | 0.6 | 0.6 | 0.5 | 0.2 | 0.1 |  | DONE | 2
29 | T29: Look into relevant code for implementing US3 (turret targeting) | Dia 0: 1.6; Dia 6: 1; Dia 7: 0.6 | DONE | 1.6
30 | T30: Look into relevant code for implementing US4 (copy and its history) | [8 empty] | DONE | 1 | bar: Dia 0; Dia 6
Esforço Completo |  | 0 | 3.5 | 1.6 | 3.1 | 2 | 1.6 | 3.2 | 0.6
Esforço Restante |  | 15.6 | 12.1 | 10.5 | 7.4 | 5.4 | 3.8 | 0.6 | 0
Burndown Ideal |  | 15.6 | 13.3714 | 11.1429 | 8.9143 | 6.6857 | 4.4571 | 2.2286 | 0

## Burndown Chart Sprint6
Sprint 6 Burndown Chart
Sprint 6
Task ID | Descrição da Tarefa | Estimativa Inicial | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23
|  | Dia 0 | Dia 1 | Dia 2 | Dia 3 | Dia 4 | Dia 5 | Dia 6 | Dia 7
31.1 | Work on implementing US3 (turret's targeting). | 2 |  | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 |  | DONE | 2 | Dinis
31.2 | Work on implementing US3 (turret's targeting). | 2 | 0.5 |  | 0.5 | 0.5 |  | 0.5 |  | DONE | 2 | Gabriela
32.1 | Work on implementing US4 (copy and its history). | 2 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  | DONE | 2 | Carolina
32.2 | Work on implementing US4 (copy and its history). | 2 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  | DONE | 2 | Manuel
33.1 | Look into what a Use Case covering US3 would look like (turret's targeting). | Dia 0: 0.5; Dia 3: 0.25; Dia 4: 0.25 | DONE | 0.5 | Dinis
33.2 | Look into what a Use Case covering US3 would look like (turret's targeting). | Dia 0: 0.5; Dia 1: 0.25; Dia 4: 0.25 | DONE | 0.5 | Gabriela
34.1 | Look into what a Use Case covering US4 would look like (copy and its history). | Dia 0: 0.5; Dia 4: 0.25; Dia 7: 0.25 | DONE | 0.5 | Carolina
34.2 | Look into what a Use Case covering US4 would look like (copy and its history). | Dia 0: 0.5; Dia 4: 0.25; Dia 7: 0.25 | DONE | 0.5 | Manuel
35 | Work on the extensive version of US1's use case (undo/redo). | Dia 0: 1; Dia 1: 0.25; Dia 2: 0.75 | DONE | 1 | Gabriel
36 | Work on the extensive version of US2's use case (liquid leak checking). | Dia 0: 1; Dia 3: 0.5; Dia 4: 0.5 | DONE | 1 | Diogo
37.1 | Work on the extensive version of US3's use case (turret's targeting). | Dia 0: 1; Dia 6: 0.5; Dia 7: 0.5 | DONE | 1 | Dinis
37.2 | Work on the extensive version of US3's use case (turret's targeting). | Dia 0: 1; Dia 5: 0.75; Dia 7: 0.25 | DONE | 1 | Gabriela
38.1 | Work on the extensive version of US4's use case (copy and its history). | [8 empty] | DONE | 1 | Carolina | bar: Dia 0; Dia 7
38.2 | Work on the extensive version of US4's use case (copy and its history). | [8 empty] | DONE | 1 | Manuel | bar: Dia 0; Dia 7
39 | Work on the sequence diagram for US1 (undo/redo). | Dia 0: 3; Dia 5: 1; Dia 6: 1; Dia 7: 1 | DONE | 3 | Gabriel
40 | Work on the sequence diagram for US2 (liquid leak checking). | Dia 0: 3; Dia 6: 2.5; Dia 7: 0.5 | DONE | 3 | Diogo
41 | Look into what a Class Diagram covering US1 would look like (undo/redo). | Dia 0: 2; Dia 1: 0.5; Dia 2: 0.5; Dia 3: 1 | DONE | 2 | Gabriel
42 | Look into what a class diagram covering US2 would look like (liquid leak checking). | Dia 0: 2; Dia 1: 0.5; Dia 2: 0.5; Dia 3: 1 | DONE | 2 | Diogo
Esforço Completo |  | 0 | 3 | 3.25 | 4.75 | 3.5 | 2 | 4.75 | 4.75
Esforço Restante |  | 26 | 23 | 19.75 | 15 | 11.5 | 9.5 | 4.75 | 0
Burndown Ideal |  | 26 | 22.2857 | 18.5714 | 14.8571 | 11.1429 | 7.4286 | 3.7143 | 0

## Burndown Chart Sprint7
Sprint 7 Burndown Chart
Sprint 5
Task ID | Descrição da Tarefa | Estimativa Inicial | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04
|  | Dia 0 | Dia 1 | Dia 2 | Dia 3 | Dia 4 | Dia 5 | Dia 6 | Dia 7 | Dia 8 | Dia 9 | Dia 10 | Dia 11
43.1 | T43: Look into what a class diagram covering US3 would look like (Swapping turret's targeting priorities). | 99 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | NOT ENOUGH WORK YET | 4.5 | Gabriela
43.2 | T43: Look into what a class diagram covering US3 would look like (Swapping turret's targeting priorities). | 99 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | NOT ENOUGH WORK YET | 4.5 | Dinis
44.1 | T44: Look into what a class diagram covering US4 would look like (Copy and Paste). | 1.5 | 2025-11-26: 0.5; 2025-11-27: 0.5; 2025-11-28: 0.5 | DONE | 1.5 | Carolina
44.2 | T44: Look into what a class diagram covering US4 would look like (Copy and Paste). | 1.5 | 2025-11-26: 0.5; 2025-11-27: 0.5; 2025-11-28: 0.5 | DONE | 1.5 | Manel
45.1 | T45: Work on the sequence diagram for US3 (Swapping turret's targeting priorities). | 99 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | NOT ENOUGH WORK YET | 5 | Gabriela
45.2 | T45: Work on the sequence diagram for US3 (Swapping turret's targeting priorities). | 99 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | NOT ENOUGH WORK YET | 5 | Dinis
46.1 | T46: Work on the sequence diagram for US4 (Copy and Paste). | 2.5 | 2025-11-28: 0.2; 2025-11-29: 0.3; 2025-11-30: 0.5; 2025-12-01: 0.5; 2025-12-02: 0.5; 2025-12-03: 0.5 | DONE | 2.5 | Carolina
46.2 | T46: Work on the sequence diagram for US4 (Copy and Paste). | 2.5 | 2025-11-28: 0.2; 2025-11-29: 0.3; 2025-11-30: 0.5; 2025-12-01: 0.5; 2025-12-02: 0.5; 2025-12-03: 0.5 | DONE | 2.5 | Dinis
47 | T47: Design and perform unit tests US1 (undo/redo) | 1.5 | 2025-11-24: 0.2; 2025-11-25: 0.2; 2025-11-26: 0.2; 2025-11-27: 0.2; 2025-11-28: 0.2; 2025-11-29: 0.5 | DONE | 1.5 | Gabriel
48 | T48: Design and perform unit tests US2 (liquid leak checking) | 1.5 | 2025-11-25: 0.5; 2025-11-26: 0.7; 2025-11-27: 0.3 | DONE | 1.5 | Diogo
49.1 | T49: Design and perform unit tests US3 (Swapping turret's targeting priorities) | 99 | 2025-12-01: 0.5; 2025-12-02: 0.5; 2025-12-03: 0.5 | NOT ENOUGH WORK YET | 1.5 | Gabriela
49.2 | T49: Design and perform unit tests US3 (Swapping turret's targeting priorities) | 99 | 2025-12-01: 0.5; 2025-12-02: 0.5; 2025-12-03: 0.5 | NOT ENOUGH WORK YET | 1.5 | Dinis
50.1 | T50: Design and perform unit tests US4 (Copy and Paste) | 2 | [11 empty] | DONE | 2 | Carolina | bar: 2025-12-01 to 2025-12-02
50.2 | T50: Design and perform unit tests US4 (Copy and Paste) | 2 | [11 empty] | DONE | 2 | Manel | bar: 2025-12-01 to 2025-12-02
51 | T51: Elaborate short report on an implementation summary of US1 (undo/redo) | 99 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | NOT ENOUGH WORK YET | 4.5 | Gabriel
52 | T52: Elaborate short report on an implementation summary of US2 (liquid leak checking) | 1 | [11 empty] | DONE | 1 | Diogo | bar: 2025-11-24
53.1 | T53: Elaborate short report on an implementation summary of US3 (Swapping turret's targeting priorities) | 1 | 2025-11-30: 0.5; 2025-12-01: 0.5 | DONE | 1 | Gabriela
53.2 | T53: Elaborate short report on an implementation summary of US3 (Swapping turret's targeting priorities) | 1 | 2025-11-30: 0.5; 2025-12-01: 0.5 | DONE | 1 | Dinis
54.1 | T54: Elaborate short report on an implementation summary of US4 (Copy and Paste) | 1.5 | 2025-11-25: 0.5; 2025-11-26: 0.5; 2025-11-27: 0.5 | DONE | 1.5 | Carolina
54.2 | T54: Elaborate short report on an implementation summary of US4 (Copy and Paste) | 1.5 | 2025-11-25: 0.5; 2025-11-26: 0.5; 2025-11-27: 0.5 | DONE | 1.5 | Manel
55.1 | T55: Additionally refine previously implemented code | 1.5 | 2025-11-25: 0.3; 2025-11-26: 0.2; 2025-11-27: 0.2; 2025-11-28: 0.3; 2025-11-29: 0.5 | DONE | 1.5 | Gabriela
55.2 | T55: Additionally refine previously implemented code | 1.5 | 2025-11-25: 0.3; 2025-11-26: 0.2; 2025-11-27: 0.2; 2025-11-28: 0.3; 2025-11-29: 0.5 | DONE | 1.5 | Gabriel
56.1 | T56: Work on a tour video of the implemented features by the team (up to 5 minutes) | 1 | 2025-12-02: 0.3; 2025-12-03: 0.5; 2025-12-04: 0.2 | DONE | 1 | Gabriel
56.2 | T56: Work on a tour video of the implemented features by the team (up to 5 minutes) | 1 | 2025-12-02: 0.3; 2025-12-03: 0.5; 2025-12-04: 0.2 | DONE | 1 | Diogo
56.3 | T56: Work on a tour video of the implemented features by the team (up to 5 minutes) | 1 | 2025-12-02: 0.2; 2025-12-03: 0.3; 2025-12-04: 0.5 | DONE | 1 | Gabriela
56.4 | T56: Work on a tour video of the implemented features by the team (up to 5 minutes) | 1 | 2025-12-02: 0.2; 2025-12-03: 0.3; 2025-12-04: 0.5 | DONE | 1 | Dinis
56.5 | T56: Work on a tour video of the implemented features by the team (up to 5 minutes) | 1 | 2025-12-02: 0.2; 2025-12-03: 0.3; 2025-12-04: 0.5 | DONE | 1 | Carolina
56.6 | T56: Work on a tour video of the implemented features by the team (up to 5 minutes) | 1 | 2025-12-02: 0.2; 2025-12-03: 0.3; 2025-12-04: 0.5 | DONE | 1 | Manel
57.1 | T57: Work on a scrum board animation video (up to 2 minutes) | 1 | 2025-12-03: 0.5; 2025-12-04: 0.5 | DONE | 1 | Gabriel
57.2 | T57: Work on a scrum board animation video (up to 2 minutes) | 1 | 2025-12-03: 0.5; 2025-12-04: 0.5 | DONE | 1 | Diogo
57.3 | T57: Work on a scrum board animation video (up to 2 minutes) | 1 | 2025-12-03: 0.5; 2025-12-04: 0.5 | DONE | 1 | Gabriela
57.4 | T57: Work on a scrum board animation video (up to 2 minutes) | 1 | 2025-12-03: 0.5; 2025-12-04: 0.5 | DONE | 1 | Dinis
57.5 | T57: Work on a scrum board animation video (up to 2 minutes) | 1 | 2025-12-03: 0.5; 2025-12-04: 0.5 | DONE | 1 | Carolina
57.6 | T57: Work on a scrum board animation video (up to 2 minutes) | 1 | 2025-12-03: 0.5; 2025-12-04: 0.5 | DONE | 1 | Manel
[14 empty] | NOT STARTED | 0
[14 empty] | NOT STARTED | 0
[14 empty] | NOT STARTED | 0
[14 empty] | NOT STARTED | 0
Esforço Completo |  | 0 | 2.2 | 4.8 | 5.8 | 5.4 | 4.7 | 4.6 | 4.5 | 7.5 | 7.9 | 9.7 | 5.4
Esforço Restante |  | 729 | 726.8 | 722 | 716.2 | 710.8 | 706.1 | 701.5 | 697 | 689.5 | 681.6 | 671.9 | 666.5
Burndown Ideal |  | 729 | 662.7273 | 596.4545 | 530.1818 | 463.9091 | 397.6364 | 331.3636 | 265.0909 | 198.8182 | 132.5455 | 66.2727 | 0