## Project Planner
Project Planner
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 47 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
TEAM MEMBER(s) | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | S1 | [11 empty] | S2 |  |  |  |  | M1 |  | S3 | [6 empty] | S4 |  |  |  |  | M2 |  | S5 | [6 empty] | S6 | [6 empty] | S7 | [9 empty] | M3
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
67286, 67763, 67804 | T1: Play the first area of the game. | 4 | 3 | 4 | 20 | 100% | bar: S2 13
67286, 67763, 67775, 67804, 68130, 68547 | T2: Read through the classes in the codebase. | 5 | 6 | 2 | 16 | 100%
67775 | T3: Define roughly functionality 1. | 8 | 1 | 3 | 4 | 100%
67763, 67775, 68547 | T4: Define roughly functionality 2. | 9 | 1 | 7 | 1 | 100%
67763, 67775, 68547 | T5: Define roughly functionality 3. | 10 | 1 | 8 | 4 | 100%
67775 | T6: Trial modification of code. | 11 | 2 | 7 | 2 | 100%
67763 | Task 7: Make feature goals more specific | 13 | 2 | 13 | 2 | 100%
67775 | Task 8: Brainstorm further features for replacement. | 13 | 2 | 15 | 3 | 100%
67775 | Task 9: Study code associated to undo/redo | 15 | 2 | 17 | 2 | 100%
68547 | Task 10: Study code associated with water piping system | 13 | 4 | 13 | 14 | 75%
67775 | Task 11: Define functionality 1 | 13 | 2 | 13 | 2 | 100%
67763 | Task 12: Define functionality 2 | 13 | 2 | 13 | 2 | 100%
67775 | Task 13 Define functionality 3 | 14 | 2 | 15 | 2 | 100%
67286 | T14.1: Revisit the read code, and find code smells. | 20 | 2 | 21 | 7 | 100%
67763 | T14.2: Revisit the read code, and find code smells. | 20 | 2 | 24 | 2 | 100%
67775 | T14.3: Revisit the read code, and find code smells. | 20 | 2 | 20 | 6 | 100%
67804 | T14.4: Revisit the read code, and find code smells. | 20 | 2 | 23 | 4 | 100%
68130 | T14.5: Revisit the read code, and find code smells. | 20 | 2 | 25 | 3 | 100%
68547 | T14.6: Revisit the read code, and find code smells. | 20 | 2 | 21 | 2 | 100%
67286 | T15.1: Document found code smells, and brainstorm possible solutions. | 22 | 3 | 26 | 1 | 100%
67763 | T15.2: Document found code smells, and brainstorm possible solutions. | 22 | 3 | 25 | 3 | 100%
67775 | T15.3: Document found code smells, and brainstorm possible solutions. | 22 | 3 | 24 | 3 | 100%
67804 | T15.4: Document found code smells, and brainstorm possible solutions. | 22 | 3 | 23 | 5 | 100%
68130 | T15.5: Document found code smells, and brainstorm possible solutions. | 22 | 3 | 27 | 1 | 100%
68547 | T15.6: Document found code smells, and brainstorm possible solutions. | 22 | 3 | 23 | 4 | 100%
67286 | T16.1: Revisit the read code, and find design patterns. | 20 | 2 | 21 | 6 | 100%
67763 | T16.2: Revisit the read code, and find design patterns. | 20 | 2 | 24 | 3 | 100%
67775 | T16.3: Revisit the read code, and find design patterns. | 20 | 2 | 24 | 3 | 100%
67804 | T16.3: Revisit the read code, and find design patterns. | 20 | 2 | 26 | 2 | 100%
68130 | T16.5: Revisit the read code, and find design patterns. | 20 | 2 | 27 | 1 | 100%
68547 | T16.6: Revisit the read code, and find design patterns. | 20 | 2 | 21 | 8 | 100%
67286 | T17.1: Find code blocks, where some design patterns may be implemented. | 20 | 2 | 21 | 5 | 100%
67763 | T17.2: Find code blocks, where some design patterns may be implemented. | 20 | 2 | 24 | 3 | 100%
67775 | T17.3: Find code blocks, where some design patterns may be implemented. | 20 | 2 | 24 | 3 | 100%
67804 | T17.4: Find code blocks, where some design patterns may be implemented. | 20 | 2 | 26 | 2 | 100%
68130 | T17.5: Find code blocks, where some design patterns may be implemented. | 20 | 2 | 27 | 4 | 100%
68547 | T17.6: Find code blocks, where some design patterns may be implemented. | 20 | 2 | 21 | 10 | 100%
67286 | T18.1: Document found design patterns, and think about possible improvements. | 23 | 3 | 25 | 6 | 100%
67763 | T18.2: Document found design patterns, and think about possible improvements. | 23 | 3 | 25 | 3 | 100%
67775 | T18.3: Document found design patterns, and think about possible improvements. | 23 | 3 | 26 | 2 | 100%
67804 | T18.4: Document found design patterns, and think about possible improvements. | 23 | 3 | 27 | 3 | 100%
68130 | T18.5: Document found design patterns, and think about possible improvements. | 23 | 3 | 27 | 0 | 100%
68547 | T18.6: Document found design patterns, and think about possible improvements. | 23 | 3 | 24 | 4 | 100%
67286 | T19.1: Revisit the read code, and study the associated metrics. | 30 | 1 | 32 | 1 | 100%
67763 | T19.2: Revisit the read code, and study the associated metrics. | 30 | 1 | 31 | 1 | 100%
67775 | T19.3: Revisit the read code, and study the associated metrics. | 30 | 1 | 31 | 1 | 100%
67804 | T19.4: Revisit the read code, and study the associated metrics. | 30 | 1 | 32 | 1 | 100%
68130 | T19.5: Revisit the read code, and study the associated metrics. | 30 | 1 | 32 | 1 | 100%
68547 | T19.6: Revisit the read code, and study the associated metrics. | 30 | 1 | 32 | 1 | 100%
67286 | T20.1: Document said metrics. | 31 | 2 | 32 | 1 | 100%
67763 | T20.2: Document said metrics. | 30 | 2 | 32 | 1 | 100%
67775 | T20.3: Document said metrics. | 30 | 2 | 32 | 1 | 100%
67804 | T20.4: Document said metrics. | 30 | 2 | 32 | 1 | 100%
68130 | T20.5: Document said metrics. | 30 | 2 | 32 | 1 | 100%
68547 | T20.6: Document said metrics. | 30 | 2 | 32 | 1 | 100%
67286 | T21.1: Revisit the read code, and choose a part of the system to work on. | 28 | 1 | 28 | 1 | 100%
67763 | T21.2: Revisit the read code, and choose a part of the system to work on. | 28 | 1 | 28 | 2 | 100%
67775 | T21.3: Revisit the read code, and choose a part of the system to work on. | 28 | 1 | 28 | 2 | 100%
67804 | T21.4: Revisit the read code, and choose a part of the system to work on. | 28 | 1 | 29 | 1 | 100%
68130 | T21.5: Revisit the read code, and choose a part of the system to work on. | 28 | 1 | 30 | 1 | 100%
68547 | T21.6: Revisit the read code, and choose a part of the system to work on. | 28 | 1 | 30 | 1 | 100%
67286 | T22.1: Develop the Use Case Diagram of the chosen system part. | 29 | 2 | 29 | 0 | 100%
67763 | T22.2: Develop the Use Case Diagram of the chosen system part. | 29 | 2 | 28 | 0 | 100%
67775 | T22.3: Develop the Use Case Diagram of the chosen system part. | 29 | 2 | 28 | 0 | 100%
67804 | T22.4: Develop the Use Case Diagram of the chosen system part. | 29 | 2 | 29 | 0 | 100%
68130 | T22.5: Develop the Use Case Diagram of the chosen system part. | 29 | 2 | 30 | 0 | 100%
68547 | T22.6: Develop the Use Case Diagram of the chosen system part. | 29 | 2 | 30 | 0 | 100%
67775 | T23: Look into what a Use case diagram covering undo/redo added feature would look like. | 34 | 3 | 36 | 1 | 100%
67763 | T24: Look into what a Use case diagram covering leakage added feature would look like. | 34 | 2 | 36 | 1 | 100%
67286, 67763, 67775, 67804, 68130, 68547 | T25: Go over milestone 2 reviews and identify issues that can be worked on. | 34 | 3 | 32 | 4 | 100%
67763 | T26: identify areas of code relating to leaks. | 34 | 1 | 34 | 1 | 100%
67775 | T27: Work on implementing US1 (Undo / Redo). | 34 | 3 | 0 | 3 | 100%
67763 | T28: Work on implementing US2 (Leaks). | 34 | 3 | 34 | 2 | 100%
67804, 68547 | T29: Look into relevant code for implementing US3 (turret targeting) | 38 | 1 | 39 | 2 | 100%
67286, 68130 | T30: Look into relevant code for implementing US4 (copy and its history) | 38 | 1 | 39 | 1.5 | 100%
67286, 68130 | T31: Work on implementing US3 (turret's targeting). | 40 | 3 | 40 | 7 | 100%
67804, 68547 | T32: Work on implementing US4 (copy and its history). | 40 | 3 | 40 | 5 | 100%
67286, 68130 | T33: Look into what a Use Case covering US3 would look like (turret's targeting). | 43 | 1 | 40 | 3 | 100%
67804, 68547 | T34: Look into what a Use Case covering US4 would look like (copy and its history). | 43 | 1 | 44 | 3 | 100%
67775 | T35: Work on the extensive version of US1's use case (undo/redo). | 40 | 3 | 40 | 1 | 100%
67763 | T36: Work on the extensive version of US2's use case (liquid leak checking). | 40 | 3 | 42 | 1 | 100%
67286, 68130 | T37: Work on the extensive version of US3's use case (turret's targeting). | 44 | 3 | 45 | 2 | 100%
67804, 68547 | T38: Work on the extensive version of US4's use case (copy and its history). | 44 | 3 | 47 | 1 | 100%
67775 | T39: Work on the sequence diagram for US1 (undo/redo). | 43 | 4 | 45 | 2 | 100%
67763 | T40: Work on the sequence diagram for US2 (liquid leak checking). | 43 | 4 | 46 | 1 | 100%
67775 | T41: Look into what a Class Diagram covering US1 would look like (undo/redo). | 44 | 3 | 40 | 2 | 100%
67763 | T42: Look into what a class diagram covering US2 would look like (liquid leak checking). | 44 | 3 | 40 | 2 | 100%
| T43: Look into what a class diagram covering US3 would look like (Swapping turret's targeting priorities). |  |  |  |  | 100%
| T44: Look into what a class diagram covering US4 would look like (Copy and Paste). |  |  |  |  | 100%
| T45: Work on the sequence diagram for US3 (Swapping turret's targeting priorities). |  |  |  |  | 100%
| T46: Work on the sequence diagram for US4 (Copy and Paste). |  |  |  |  | 100%
| T47: Design and perform unit tests US1 (undo/redo) |  |  |  |  | 100%
| T48: Design and perform unit tests US2 (liquid leak checking) |  |  |  |  | 100%
| T49: Design and perform unit tests US3 (Swapping turret's targeting priorities) |  |  |  |  | 100%
| T50: Design and perform unit tests US4 (Copy and Paste) |  |  |  |  | 100%
| T51: Elaborate short report on an implementation summary of US1 (undo/redo) |  |  |  |  | 100%
| T52: Elaborate short report on an implementation summary of US2 (liquid leak checking) |  |  |  |  | 100%
| T53: Elaborate short report on an implementation summary of US3 (Swapping turret's targeting priorities) |  |  |  |  | 100%
| T54: Elaborate short report on an implementation summary of US4 (Copy and Paste) |  |  |  |  | 100%
| T55: Additionally refine previously implemented code |  |  |  |  | 100%
| T56: Work on a tour video of the implemented features by the team (up to 5 minutes) |  |  |  |  | 100%
| T57: Work on a scrum board animation video (up to 2 minutes) |  |  |  |  | 100%