## Week 1
Mindustry Project
1.1 Information Gathering
US3: Define 3 new functionalities
1.2 Brainstorming functionalities
1. New functionality planning
US1: General grasp of game mechanics
US2: Read the codebase
T1: Play the first area of the game
T2:
Read through the classes in the codebase
T3:
Define roughly functionality 1
T6:
Trial modification of code
T4:
Define roughly functionality 2
T5:
Define roughly functionality 3

## Week 2
Mindustry Project
1.1 Information Gathering
US4: Brainstorm potential functionalities
1.2 Brainstorming functionalities
1. New functionality planning
US1: General grasp of game mechanics
US2: Read the codebase
T1: Play the first area of the game
T2:
Read through the classes in the codebase
T11: Define functionality 1
T12: Define functionality 2
T13: Define functionality 3
T7: Make feature goals more specific.
2. Implementation
2.1 Code study
US5: Study the code around potential new features
T10: Water piping system associated code.
T9: Undo/redo feature associated code.
T8: Brainstorm further features for replacement

## Week 3
Mindustry Project
1.1 Information Gathering
1. New functionality planning
US1: General grasp of game mechanics
T1: Play the first area of the game
2. Implementation
2.1 Code study
US5: Study the code around potential new features
T10: Water piping system associated code.
T14: Revisit the read code, and find code smells.
T15: Document found code smells, and brainstorm possible solutions.
3. Code Analysis
3.1 Code Smells
3.2 Design Patterns
US7: Identify and document design patterns
US6: Identify, document and propose solutions for code smells
T16: Revisit the read code, and find design patterns.
T17: Find code blocks, where some design patterns may be implemented.
T18: Document found design patterns, and think about possible improvements.

## Week 4
Mindustry Project
T14: Revisit the read code, and find code smells.
T15: Document found code smells, and brainstorm possible solutions.
3.1 Code Smells
3.2 Design Patterns
US7: Identify and document design patterns
US6: Identify, document and propose solutions for code smells
T16: Revisit the read code, and find design patterns.
T17: Find code blocks, where some design patterns may be implemented.
T18: Document found design patterns, and think about possible improvements.
3. Code Analysis
US8: Document code metrics
3.3 Code Metrics
T19: Revisit the read code, and study the associated metrics.
T20: Document said metrics.
3.4 Use cases
US9: Document use case(s)
T21: Revisit the code and choose a system.
T22: Develop the Use Case Diagram of the chosen system part.

## Week 5
Mindustry Project
2. Implementation
2.1 Code study
3. Code Analysis
3.4 Use Cases
3.6 Sequence Diagrams
US11: Plan Use cases based on current implementations
US10: Go through reviews
2.2 Code Implementation
3.5 Go over Reviews
US12: Start sequence diagrams based on potential Use Cases
T28: work on implementing minimap identification of player team leaks.targeting)
T27: Work on implementing US1 (Undo / Redo).
T26: identify areas of code relating to leaks.
T25: Go over milestone 2 reviews and identify issues that can be worked on.
T24: Look into what a Use case diagram covering leakage added feature would look like.
T23: Look into what a Use case diagram covering undo/redo added feature would look like.
T29: Look into relevant code for implementing US3 (turret targeting)
T30: Look into relevant code for implementing US4 (copy and its history)
US3: turret targetting
US4: copying and history
US1: Undo Redo
US2: Minimap leakage identification

## Week 6
Mindustry Project
2. Implementation
3. Code Analysis
2.2 Code Implementation
US13: Implement an US defined in milestone1
T31: Work on implementing US3 (turret's targeting).
T32: Work on implementing US4 (copy and its history).
3.6 Sequence Diagrams
3.4 Use Cases
US13: Illustrate an US implementation
US:14 Design an US class diagram
3.7 Class Diagrams
T33: Look into what a Use Case covering US3 would look like (turret's targeting).
T34: Look into what a Use Case covering US4 would look like (copy and its history).
T36: Work on the extensive version of US2's use case (liquid leak checking).
T35: Work on the extensive version of US1's use case (undo/redo).
T40: Work on the sequence diagram for US2 (liquid leak checking).
T39: Work on the sequence diagram for US1 (undo/redo).
T37: Work on the extensive version of US3's use case (turret's targeting).
T38: Work on the extensive version of US4's use case (copy and its history).
T41: Look into what a class diagram covering US1 would look like (undo/redo).
T42: Look into what a class diagram covering US2 would look like (liquid leak checking).

## Week 7
U+0020 | U+0021
Mindustry Project
2. Implementation
3. Code Analysis
2.2 Code Implementation
US13: Refine code implemented previously
T55: Additionally refine previously implemented code
3.6 Sequence Diagrams
3.4 Use Cases
US:15 Design an US class diagram
3.7 Class Diagrams
T42: Look into what a class diagram covering US2 would look like (liquid leak checking).
US14: Design a sequence diagram
T45: Work on the sequence diagram for US3 (Swapping turret's targeting priorities).
T46: Work on the sequence diagram for US4 (Copy and Paste).
3.8 Unit Tests
US16: Design Unit Tests
T47: Design and perform unit tests US1 (undo/redo)
T50: Design and perform unit tests US4 (Copy and Paste)
T49: Design and perform unit tests US3 (Swapping turret's targeting priorities)
T48: Design and perform unit tests US2 (liquid leak checking)
3.9 Implementation Summary
US17: Report on Implementation
T51: Elaborate short report on an implementation summary of US1 (undo/redo)
T54: Elaborate short report on an implementation summary of US4 (Copy and Paste)
T53: Elaborate short report on an implementation summary of US3 (Swapping turret's targeting priorities)
T52: Elaborate short report on an implementation summary of US2 (liquid leak checking)
3.10 Tour Video
3.11 Scrum Board Animation
US17: Report on Implementation
US17: Report on Implementation
T56: Work on a tour video of the implemented features by the team (up to 5 minutes)
T57: Work on a scrum board animation video (up to 2 minutes)